Bardsey Neighbourhood Plan Steering Committee

Minutes of the Meeting held on 18.5.16.

Present :- Jane Ambrose (JA),Mike Bosomworth (MB), Lyndsay Burns (LB), Ian Frankland (IF), June Gallant (JG),  Chris Sidle(CS), Ed Stentiford (ES), and Martin Ward (MW)

Apologies: Stephen Bucknell and Jane Ingham.

.                                                           Declarations of any Pecuniary and Other Interests  None.

Minutes of Meeting held on 20.4.16.  These were approved.

Matters Arising :-

.Revised NDP document  - CS reported that this is now virtually complete. He had himself re-done 2 of the maps and has included a page of acknowledgements at the end. All members of the SC are happy with the revised document.

Sustainability Assessment :- There was no further news on this.

.Environmental Sustainability Assessment   No news on this either. IF said LCC needed a reminder.

Proof Reading  - Completed.

Arrangements for Printing and Distribution of Document and Letter to Residents. - . CS has obtained quotations from Write Design of Wetherby of £95 for printing the letter (not yet written), £85 for the envelopes, and £65 for assembling the contents. All printing must be completed by June 10th for delivery between June 10th and 17th. Six weeks should then be allowed before a Drop In session. It was agreed to pay in addition for 30 hard copies to be printed.(Write Design had quoted £150 for 25 copies). All members of the SC should have one, and others should be placed in the Village Hall, the Callister Hall, the Bingley Arms, the Sports Club, the School, Hairdresser’s, Wetherby library, Collingham surgery, the Church, the One Stop Centre in Wetherby , the Tennis and Bowling Clubs, EK Methodist Church, and Scarcroft Golf Club.

An approval for use of Ordnance Survey maps will be required. David Gluck will be approached in the first instance on this. (Action JG)

CS had one query over a photograph of an affordable home. He wished to know the views of the SC as to their preference between a photo of manageable homes in the draft NP or a shot of affordable homes which it had been proposed should replace it. The SC expressed a preference for retaining the original photo unless a better and more recent example of manageable homes  could be found locally, and suggested a suitable group of properties at Whinmoor.(Action CS)

Drop In Session – Preferred dates are July 9th or 16th if Village Hall or Callister Hall are free from 10 - 4 .An advert for the occasion should be placed in the Wetherby News. A continuous slide show should be arranged in the Hall on the day and the 5 or 6 central pages, showing the 6 policies should be on display. Tea, coffee and biscuits should be served..(Action ES/ CS)

Boundary Change for Bardsey NDP  As there  has still been no reply from Steve Wilkinson, JG has e mailed Cllr Matthew Robinson asking him to help speed up proceedings.

Review of Project Plan. IF has made some revisions to this. :-

- Pre – Submission Consultation – 17th June 16 to 29th July 16

- LA to appoint Examiner – 31st August 16 to 12thOctober 16

- Examination – 14th November 16 to 12th December 16.

- Publish Examination Report – 14th January 17 to 18th February 17.

- Publication of   Referendum – 18th February 17 to end March 17

- Hold Referendum – April 17.

- Publish Referendum Result – May 17.

- NP  Made – June 17.

Resources and Needs  - ES is in process of compiling a shopping list of likely expenditure during the next 6 months, to be sent to Locality. (Action ES)

.A.O.B

1.MB reported that he has obtained the forms required to apply for the designation of the old railway line as a public right of way. He will ring up for further information on this.(Action MB)

2. JA reported that the School now owns its land under the new Trust status, and is planning to open a nursery in September.

3. JG mentioned that she had noted the inclusion of a reference to a specific LCC core strategy proposal in the draft plan of another village. IF will look into the necessity for this, but it was agreed that this could always be added at a later stage and should not affect circulation to the village. (Action IF)

4. It was agreed that steps should be taken to have the Bingley Arms listed as an asset of community value.

Dates of next 2 Meetings :- Wednesday 15th June and Wednesday 20th July.

.

BPC St. Co. May 16 Mins.