Bardsey Neighbourhood Plan Steering Committee

Notes of special meeting held on 15th August in the Committee Room of the Village Hall.

Present:  Mike Bosomworth(MB), Lindsay Burns(LB), Jack Cairns(JC), June Gallant(JG), Ed Stentiford(ES) ,  Lance Tattersall(LC)..

Apologies:Jane Ambrose(JA),  Ian Frankland (IF), Jane Ingham (JI) and Geoffrey Tatman (GT).

Plans for Open Meeting  All discussion was focused on this. Between meetings it had been suggested by JC that it would be more realistic to move this date to Saturday November 10th to allow further time for preparation. This was agreed .

Timing – Preference was for 2 sessions – 10- 1pm and 1-4pm., with Question & Answer sessions at 12.30 – 1, and 3.30 – 4.

Key Points to convey – Essential to establish credibility of committee – methods of assessing each site and calculating individual site scores relating to essential features:-

- Maintaining essential character of village

- Core development

- Impact of each on surroundings

- Avoidance of ribbon development

- Avoidance of interference with panoramic views

- Unobtrusive from view.

Future School Building – Research between meetings had established that on the preferred site 1027 (N) , given the amount of land required for school building, parking and playing fields, there might be little space for housing. Considered essential for School Governors to indicate their preferences for future school site before making proposals to village.  JG to ask JA to make this an agenda item for next Governors Meeting. Governors to be asked what they are looking for in a Neighbourhood Plan.

Need to re-visit Scoring Criteria for individual sites – This to be an agenda item for September meeting following any fresh information from Andy Birkbeck re general site allocations in NE Leeds at meeting on September 6th. The likely numbers of houses on 1027N also to be looked at again

Need for Graphics – Jason Cooke to be asked by ES if he is willing to assist.

Method of collecting feedback from public – Suggested that names of all attending be taken at door but feedback comments remain anonymous. Visitors from outside Bardsey be permitted to attend but only residents of Bardsey be allowed to vote. Preference for voting age to be restricted to those over 16 . JG to check with Andy Birkbeck.

Display boards for each site to be set up and responses possibly made with varying coloured dots, on the display boards and  forms would also be available for individual written comments on the sites and the scheme overall. . It was thought better id no forms to be taken home for completion as we were unlikely to get as many returns.

Advice on the exact format to be taken from residents with expertise in this area (ES to check offers of help from residents for expertise)

Arrangements in the Hall

Tables and chairs to be set up. Some refreshments desirable. Suggested VH Committee sell these (ES to approach Village Hall Committee).

Possibility pf producing Artist’s Impression of Sites. – JC suggested this would be helpful to public. LB said that, whilst agreeing, he considered the idea should be put to the consultants for the landowners with the suggestion this could improve chances for inclusion of their sites. Suggested top 3 site owners be approached. Architect’s work for each would need to be acknowledged.

The initial ‘skeleton’ draft of the Neighbourhood Plan – It was considered useful if an outline plan was available for the end of September incorporating the key issues and the historical context – ES and JC to work on producing this.

Types of Housing considered desirable – Some affordable housing necessary(20%))but unlikely to be popular with nearby residents. Bungalows considered undesirable by developers as being land hungry. Retirement apartments , possibly some sheltered, considered desirable for Bardsey and could be financially viable. Possibility of putting forward a non SHLAA site for these- a windfall site. Catholic Church site would be suitable if SHLAA site used.

Time Line

- 14th September – Copy date for the October Newsletter to provide early warning of the public meeting .  N.B. Some work on this required beforehand .

- 19th October – Copy date for the November Newsletter – either an ad or a flyer or both with full details to accompany the Newsletter.

- Date for November Steering Committee Meeting – Wednesday November 14th (2nd Wednesday in month.) – brought forward in order to hold a post mortem on the public meeting whilst it is fresh in the mind.

Notes Aug. St. Com.